## NPA Relief Activity Status
NPA Relief Planning Status Report File Dated:05/20/2024
NPA | 206 | 213/323 | 281/346/713/832 | 313 | 318 | 334 | 347/718/917/929 | 423 | 507 | 530 | 559 | 657/714 | 662 | 734 | 864 | 970
Jurisdiction | WA | CA | TX | MI | LA | AL | NY | TN | MN | CA | CA | CA | MS | MI | SC | CO
Date Relief Need Identified by NANPA | 12/19/2022 | 06/29/2022 | 03/14/2023 | 09/27/2022 | 01/31/2023 | 09/29/2023 | 03/13/2024 | 09/12/2022 | 06/20/2022 | 08/03/2022 | 11/23/2022 | 03/19/2024 | 09/14/2023 | 06/02/1999 | 02/24/2022 | 03/29/2023
Date NANPA Notified Industry/Regulators | 12/19/2022 | 06/29/2022 | 03/14/2023 | 09/27/2022 | 01/31/2023 | 09/29/2023 | 03/13/2024 | 09/12/2022 | 06/20/2022 | 08/03/2022 | 11/23/2022 | 03/19/2024 | 09/14/2023 | 06/02/1999 | 02/24/2022 | 03/29/2023
Exhaust Date upon Declaration
Current Exhaust Date | 1Q2027 | 1Q2026 | 3Q2025 | 4Q2027 | 1Q2026 | 3Q2026 | 4Q2026 | 3Q2025 | 2Q2025 | 2Q2025 | 3Q2025 | 1Q2027 | 3Q2026 | 1Q2030 | 3Q2024 | 1Q2026
Forecasted Exhaust Date | 1Q2027 | 1Q2026 | 3Q2025 | 4Q2027 | 1Q2026 | 3Q2026 | 4Q2026 | 3Q2025 | 2Q2025 | 2Q2025 | 3Q2025 | 1Q2027 | 3Q2026 | 1Q2030 | 3Q2024 | 1Q2026
Relief Status | Active | Active | Active | Active | Active | Active | Active | Active | Active | Active | Active | Active | Active | Suspended | Active | Active
Number of Remaining NXXs | 45 | 75/1 | 0/138/0/0 | 43 | 32 | 33 | 0/0/8/171 | 29 | 22 | 21 | 36 | 209/2 | 31 | 74 | 13 | 34
Number of NXXs Unavailable | 17 | 14/15 | 14/14/14/14 | 15 | 30 | 21 | 17/21/16/14 | 23 | 22 | 18 | 16 | 14/14 | 16 | 29 | 18 | 14
Initial Relief Planning Meeting Notice Date | 12/19/2022 | 06/29/2022 | 03/14/2023 | 09/27/2022 |  | 09/29/2023 | 03/13/2024 | 09/12/2022 | 06/20/2022 | 08/03/2022 | 11/23/2022 | 03/19/2024 | 09/14/2023 | 06/02/1999 | 02/24/2022 | 03/29/2023
IPD Distribution | AL: 09/29/2023; NY: 03/13/2024; TN: 09/12/2022; MN: 06/20/2022; CA: 11/23/2022; MS: 09/14/2023; MI: 06/16/1999
Actual Filing Date with Regulator | 02/16/2023 | 08/25/2022 | 05/11/2023 | 11/16/2022 |  | 12/07/2023 |  | 11/18/2022 | 08/23/2022 | 09/30/2022 | 01/26/2023 |  | 11/16/2023 |  | 04/13/2022 | 05/31/2023
Requested Implementation Date
Requested Relief Type |  | Overlay | Overlay | Overlay |  | Overlay |  | Overlay | Overlay | Overlay | Overlay |  | Overlay |  | Overlay | Overlay
Requested Approval Date | 06/30/2024 | 08/31/2023 | 12/31/2023 | 05/31/2023 |  | 08/31/2024 |  | 09/30/2023 | 05/31/2023 | 12/31/2023 | 09/30/2023 |  | 11/30/2024 |  | 11/30/2022 | 06/30/2024
Approval Date | 06/15/2023 | 03/16/2023 | 10/12/2023 | 05/18/2023 | 05/05/2023 | 03/05/2024 |  | 05/08/2023 | 04/06/2023 | 06/08/2023 | 12/14/2023 |  |  | 09/12/2001 | 09/27/2022 | 12/11/2023
Approved Relief Type | Overlay | Overlay | Overlay | Overlay | Overlay | Overlay |  | Overlay | Overlay | Overlay | Overlay |  |  | Overlay | Overlay | Overlay
Start of Permissive Dialing | MI: 04/07/2025; LA: 02/24/2025; TN: 08/05/2024; MN: 01/30/2024; CA: 08/26/2024; SC: 01/19/2024
Mandatory Dialing | MI: 10/07/2025; LA: 08/25/2025; TN: 02/05/2025; MN: 07/30/2024; CA: 01/19/2025; SC: 07/19/2024
Approved Implementation Date (Split - End of Recorded Announcement)
Approved Implementation Date (Overlay - Earliest effective date for code assignment) | 06/10/2025 | 11/01/2024 | 01/23/2025 | 11/07/2025 | 09/25/2025 |  |  | 03/05/2025 | 08/30/2024 | 01/31/2025 | 03/26/2025 |  |  |  | 08/19/2024 | 07/07/2025
New NPA code(s) assigned | 564 | 738 | 621 | 679 | 457 | 483 |  | 729 | 924 | 837 | 357 |  |  | 679 | 821 | 748
First Scheduled Implementation Meeting | 07/18/2023 | 04/25/2023 | 11/17/2023 | 06/26/2023 | 06/06/2023 | 04/18/2024 |  | 07/06/2023 | 05/23/2023 | 07/19/2023 | 01/16/2024 |  |  |  | 11/08/2022 | 01/26/2024
Planning Letter Published | 08/03/2023 PL-620 | 05/16/2023 PL-614 | 12/06/2023 PL- 623 | 02/01/2000 PL-209 04/24/2000 PL-227 07/13/2023 PL-618 | 06/23/2023 PL-617 |  |  | 07/24/2023 PL-619 | 06/12/2023 PL-616 | 08/08/2023 PL-621 | 02/06/2024 PL-624 |  |  | 02/01/2000 PL-209 04/24/2000 PL-227 | 11/28/2022 PL-606 | 02/13/2024 PL-625
Rationing Date (PL #)
Jeopardy Declared (PL #)
In Rationing (Y/N) | bar: WA to CO
Monthly Rationing
Note | 206-1 | 213/323-1 | 281/346/713/832-1 | 313-1 | 318-1 | 334-1 | 347/718/917/929-1 | 423-1 | 507-1 | 530-1 | 559-1 | 657/714-1 | 662-1 | 734-1 | 864-1 | 970-1

## Notes
206-1 | Per Docket UT-143787, Order 01, the 564 NPA will overlay all of western Washington (206, 253, 360 and 425), with telephone numbers in the 564 NPA available for assignment in 206, 253, 360 and 425 NPAs only when those NPAs are nearing exhaust to ensure efficient use of number resources. On February 16, 2023, NANPA filed a letter on behalf of the industry requesting approval from the WUTC to begin the implementation phase of the 206 and the 564 NPA overlay.
213/323-1
281/346/713/832-1
313-1 | Commission approved an overlay NPA relief code covering both the 313 & 734 NPAs on 9/7/2001. Due to elapsed time, Industry will meet on 10/19/2022 to revise implementation time frame and submit a new Petition to the Commission. Commission approved revised implementation schedule in new Petition on 5/18/23.
318-1 | February 1, 2023 Louisiana Public Service Commission Staff opened Docket No. U-36659,issuing Notice of Proceeding, Preliminary Staff Report and Proposed Recommendation, and Request for Comments for the 318 NPA. The proposed recommendation is that the Commission approve an overlay plan over a geographic split for the 318 NPA. May 5, 2023, in Docket No. U-36659, the Louisiana Public Service Commission approved all-services distributed overlay.
334-1
347/718/917/929-1
423-1
507-1
530-1
559-1
657/714-1
662-1
734-1 | 1) Commission approved an overlay NPA relief code covering both the 313 & 734 NPAs. 2)The new code will be activated 6 months before exhaust. NANPA to convene an implementation meeting to determine implementation schedule when either 313 or 734 NPA is within 12 months to exhaust.
864-1
970-1