## NpaTriggerReport
NPA Relief Planning Triggers Report File Dated:05/20/2024
NPA | Location |  | Description of NANPA Action & Trigger Point | Status
253 | WA |  | Per Docket UT-143787, Order 01, the 564 NPA will overlay all of western Washington (206, 253, 360 and 425), with telephone numbers in the 564 NPA available for assignment in 206, 253, 360 and 425 NPAs only when those NPAs are nearing exhaust to ensure efficient use of number resources. | Open 2024.1 NRUF projects exhaust at 1Q2056
425 | WA |  | Per Docket UT-143787, Order 01, the 564 NPA will overlay all of western Washington (206, 253, 360 and 425), with telephone numbers in the 564 NPA available for assignment in 206, 253, 360 and 425 NPAs only when those NPAs are nearing exhaust to ensure efficient use of number resources. | Open 2024.1 NRUF projects exhaust at 2Q2038
734 | MI |  | Per Opinion and Order, Case No. U-12743, when the 734 area code is within 12 months of NXX code exhaust, NANPA should notify the Commission of that fact and meet with relevant members of the Industry to establish a schedule for the implementation of permissive and mandatory dialing. | Open 2024.1 NRUF projects exhaust at 1Q2030
870 | AR |  | Industry agreement was reached during an implementation meeting on March 9, 2022, for the industry to begin network preparation and customer education for the boundary elimination overlay of the Arkansas 870, 501, and 479 NPAs in the first quarter of 2025. The boundary elimination overlay will be implemented by the third quarter of 2027. NANPA will convene a second implementation meeting six months prior to the start of network preparation or in the third quarter of 2024. | Open 5 NXX Codes remain available 2024.1 NRUF projects exhaust at 3Q2082
501 | AR |  | Industry agreement was reached during an implementation meeting on March 9, 2022, for the industry to begin network preparation and customer education for the boundary elimination overlay of the Arkansas 870, 501, and 479 NPAs in the first quarter of 2025. The boundary elimination overlay will be implemented by the third quarter of 2027. NANPA will convene a second implementation meeting six months prior to the start of network preparation or in the third quarter of 2024. | Open 167 NXX Codes remain available 2024.1 NRUF projects exhaust at 4Q2035
479 | AR |  | Industry agreement was reached during an implementation meeting on March 9, 2022, for the industry to begin network preparation and customer education for the boundary elimination overlay of the Arkansas 870, 501, and 479 NPAs in the first quarter of 2025. The boundary elimination overlay will be implemented by the third quarter of 2027. NANPA will convene a second implementation meeting six months prior to the start of network preparation or in the third quarter of 2024. | Open 257 NXX Codes remain available 2024.1 NRUF projects exhaust at 2Q2036