## Update Date
File last updated on 08/05/22

## AK
Milestones for 907 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| AK | 907 |  | 42
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 20
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 16
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 15
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 16
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 16

## AL
Milestones for 251 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| AL | 251 |  | 50
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 47
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 46
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 44
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 44
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 36

## AR
Milestones for 501 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| AR | 501 |  | 40
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 42
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 43
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 40
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 41
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 36

## AZ
Milestones for 480 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| AZ | 480 |  | 40
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 39
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 38
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 33
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 36
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 29
Milestones for 520 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| AZ | 520 |  | 52 |  | 0
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 49
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 48
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 42
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 45
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 37
Milestones for 928 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| AZ | 928 |  | 55
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 54
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 54
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 48
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 50
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 46

## CA
Milestones for 209 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| CA | 209 |  | 54
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 51
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 51
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 47
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 52
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 42
Milestones for 530 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| CA | 530 |  | 68
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 57
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 58
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 53
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 57
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 47
Milestones for 562 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| CA | 562 |  | 52
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 50
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 50
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 48
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 50
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 44
Milestones for 626 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| CA | 626 |  | 53
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 52
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 51
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 47
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 51
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 43
Milestones for 650 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| CA | 650 |  | 49
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 48
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 48
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 44
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 47
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 39
Milestones for 707 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| CA | 707 |  | 57
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 52
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 52
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 48
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 51
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 43
Milestones for 925 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| CA | 925 |  | 48
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 46
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 47
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 42
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 45
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 36
Milestones for 949 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| CA | 949 |  | 53
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 49
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 49
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 45
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 48
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 39
Milestones for 951 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| CA | 951 |  | 50
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 50
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 49
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 46
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 49
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 41

## CO
Milestones for 719 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| CO | 719 |  | 64
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 58
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 58
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 55
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 58
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 45
Milestones for 970 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| CO | 970 |  | 65
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 57
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 58
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 52
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 53
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 46

## DE
Milestones for 302 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| DE | 302 |  | 43
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 37
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 37
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 35
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 37
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 29

## FL
Milestones for 321 NPA (Brevard County Only) | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| FL | 321 |  | 48
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 45
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 45
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 41
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 42
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 37
Milestones for 352 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| FL | 352 |  | 48
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 44
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 44
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 39
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 43
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 35
Milestones for 561 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| FL | 561 |  | 59
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 47
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 47
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 41
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 45
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 38
Milestones for 941 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| FL | 941 |  | 52
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 45
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 45
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 42
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 45
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 37

## GA
Milestones for 478 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| GA | 478 |  | 48
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 50
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 50
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 46
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 48
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 39
Milestones for 912 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| GA | 912 |  | 58
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 55
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 55
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 48
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 51
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 43

## GU
Milestones for 671 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| GU | 671 |  | 10
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 3
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 2
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 4
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 4
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 2

## HI
Milestones for 808 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| HI | 808 |  | 27
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 22
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 22
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 22
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 22
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 20

## IA
Milestones for 319 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| IA | 319 |  | 81
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 70
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 67
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 61
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 62
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 55
Milestones for 515 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| IA | 515 |  | 69
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 55
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 52
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 49
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 51
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 44

## IL
Milestones for 309 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| IL | 309 |  | 71
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 61
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 61
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 58
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 59
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 49
Milestones for 618 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| IL | 618 |  | 58
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 55
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 55
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 52
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 54
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 46
Milestones for 708 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| IL | 708 |  | 43
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 41
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 42
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 37
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 40
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 1/8/2022* |  | 34
*Note:10-digit dialing was completed on 1/8/22 due to the NPA relief Implementation schedule for the 464/708 NPA All-Services Distributed Overlay

## IN
Milestones for 219 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| IN | 219 |  | 43
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 41
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 42
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 38
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 42
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 35
Milestones for 574 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| IN | 574 |  | 46
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 43
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 45
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 39
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 41
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 39

## KS
Milestones for 620 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| KS | 620 |  | 74
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 70
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 70
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 64
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 65
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 50
Milestones for 785 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| KS | 785 |  | 70
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 61
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 62
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 57
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 56
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 47

## KY
Milestones for 859 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| KY | 859 |  | 50
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 44
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 43
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 40
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 43
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 36

## LA
Milestones for 337 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| LA | 337 |  | 46
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 45
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 45
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 38
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 40
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 33
Milestones for 504 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| LA | 504 |  | 44
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 43
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 42
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 37
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 38
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 33

## MI
Milestones for 616 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| MI | 616 |  | 52
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 50
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 50
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 44
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 46
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 41
Milestones for 810 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| MI | 810 |  | 44
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 44
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 44
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 40
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 43
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 37
Milestones for 906 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| MI | 906 |  | 33
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 41
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 42
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 36
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 38
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 33
Milestones for 989 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| MI | 989 |  | 56
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 53
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 55
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 50
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 52
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 48

## MN
Milestones for 218 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| MN | 218 |  | 72
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 78
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 75
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 68
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 67
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 43
Milestones for 952 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| MN | 952 |  | 46
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 48
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 46
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 44
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 44
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 38

## MO
Milestones for 314 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| MO | 314 |  | 39
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 44
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 44
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 40
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 43
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 36
Milestones for 417 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| MO | 417 |  | 56
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 62
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 58
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 58
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 56
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 52
Milestones for 660 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| MO | 660 |  | 56
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 60
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 61
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 53
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 59
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 48
Milestones for 816 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| MO | 816 |  | 55
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 56
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 56
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 53
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 56
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 45

## MS
Milestones for 662 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| MS | 662 |  | 59
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 52
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 52
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 48
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 51
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 46

## MT
Milestones for 406 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| MT | 406 |  | 64
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 50
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 47
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 49
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 49
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 45

## NC
Milestones for 910 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| NC | 910 |  | 56
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 48
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 50
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 49
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 49
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 45

## NH
Milestones for 603 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| NH | 603 |  | 51
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 48
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 48
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 45
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 46
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 38

## NJ
Milestones for 856 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| NJ | 856 |  | 55
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 50
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 50
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 44
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 47
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 41
Milestones for 908 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| NJ | 908 |  | 65
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 50
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 50
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 45
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 48
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 40

## NM
Milestones for 505 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| NM | 505 |  | 48
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 44
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 45
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 42
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 43
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 36
Milestones for 575 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| NM | 575 |  | 53
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 46
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 46
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 43
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 44
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 39

## NV
Milestones for 775 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| NV | 775 |  | 46
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 48
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 49
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 46
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 46
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 40

## NY
Milestones for 516 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| NY | 516 |  | 59
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 54
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 54
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 47
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 51
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 44
Milestones for 607 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| NY | 607 |  | 56
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 65
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 65
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 59
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 60
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 56
Milestones for 716 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| NY | 716 |  | 61
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 59
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 59
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 53
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 54
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 50
Milestones for 845 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| NY | 845 |  | 74
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 64
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 64
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 58
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 56
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 52
Milestones for 914 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| NY | 914 |  | 61
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 53
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 53
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 47
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 50
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 42
41

## OH
Milestones for 440 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| OH | 440 |  | 48
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 51
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 51
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 45
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 47
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 41
Milestones for 513 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| OH | 513 |  | 44
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 40
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 39
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 36
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 39
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 33

## SD
Milestones for 605 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| SD | 605 |  | 86
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 65
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 67
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 64
0
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 65
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 57

## TN
Milestones for 731 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| TN | 731 |  | 46
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 49
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 49
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 46
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 46
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 42
Milestones for 865 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| TN | 865 |  | 49
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 46
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 47
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 42
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 43
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 39

## TX
Milestones for 254 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| TX | 254 |  | 56
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 53
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 52
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 48
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 51
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 43
Milestones for 361 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| TX | 361 |  | 50
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 47
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 46
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 42
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 44
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 38
Milestones for 409 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| TX | 409 |  | 46
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 42
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 41
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 38
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 39
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 34
Milestones for 806 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| TX | 806 |  | 49
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 52
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 48
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 43
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 45
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 39
Milestones for 830 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| TX | 830 |  | 56
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 55
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 54
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 50
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 53
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 45
Milestones for 915 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| TX | 915 |  | 36
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 39
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 39
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 35
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 38
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 32
Milestones for 940 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| TX | 940 |  | 67
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 54
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 52
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 48
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 50
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 44

## VA
Milestones for 276 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| VA | 276 |  | 48
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 48
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 48
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 44
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 45
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 38
Milestones for 804 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| VA | 804 |  | 43
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 45
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 45
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 41
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 42
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 35

## VT
Milestones for 802 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| VT | 802 |  | 45
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 40
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 39
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 38
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 39
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 32

## WA
Milestones for 509 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| WA | 509 |  | 63
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 57
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 57
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 55
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 57
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 49

## WI
Milestones for 262 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| WI | 262 |  | 45
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 53
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 53
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 50
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 53
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 48
Milestones for 414 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| WI | 414 |  | 37
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 42
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 42
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 38
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 41
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 37
Milestones for 608 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| WI | 608 |  | 84
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 84
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 84
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 81
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 84
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 76
Milestones for 920 NPA | State | NPA | Milestone Completion Due date | Total OCNs | Total # of OCN responses
| WI | 920 |  | 68
Milestone 8: Deadline to send first customer notice |  |  | 2021-03-25 |  | 72
Milestone 15: Carrier deadline to implement permissive 10-digit dialing |  |  | 2121-04-24 |  | 71
Milestone 23: Deadline to send second customer notice |  |  | 2021-09-24 |  | 68
Milestone 24: Deadline for 10-digit signaling transition |  |  | 2021-09-24 |  | 70
Milestone 33: Carrier deadline to implement mandatory 10-digit dialing |  |  | 2022-07-15 |  | 66